## L3 input
Project Name |  | Demo Vehicle Programme | [10 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  | DVP-2026 | SoP | Wk 1, 2026 | [8 empty] | 1 | 2026 | 52 | 2030
Description |  | Electrical and electronics sub-plan. | [10 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  | L3 Electronics Plan |  | Plan ID | L3_Electronics |  | Last updated | 2026-08-04
| No. | Activity / Event | Responsible | Location | Start Wk | Start Yr | End Wk | End Yr | Tracker | Status | Comments / Notes | Dependencies
| 1 | ECU hardware freeze | N. Patel | Pune | 11 | 2026 | 15 | 2026 |  | Aligned |  | L2_Powertrain-1
| 2 | Harness routing | N. Patel | Pune | 16 | 2026 | 21 | 2026 |  | Planned |  | L3_Electronics-1
| 3 | Software integration | T. Olsen | Remote | 22 | 2026 | 29 | 2026 |  | Dependency |  | L3_Electronics-2; L4_Quality-1
| 4 | EMC validation | T. Olsen | Gothenburg | 30 | 2026 | 35 | 2026 |  | Risk |  | L3_Electronics-3
| 5 | Electronics release | N. Patel | Pune | 37 | 2026 | 41 | 2026 |  | TBD |  | L3_Electronics-4
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## L3 time plan
No. | Activity / Event | Responsible | Location | Status