## L4 input
Project Name |  | Demo Vehicle Programme | [10 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  | DVP-2026 | SoP | Wk 1, 2026 | [8 empty] | 1 | 2026 | 52 | 2030
Description |  | Material flow and logistics detail plan. | [10 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  | L4 Logistics Plan |  | Plan ID | L4_Logistics |  | Last updated | 2026-06-20
| No. | Activity / Event | Responsible | Location | Start Wk | Start Yr | End Wk | End Yr | Tracker | Status | Comments / Notes | Dependencies
| 1 | Packaging concept | E. Silva | Greensboro | 18 | 2026 | 22 | 2026 |  | Completed |  | L2_Bodyshop-2
| 2 | Inbound flow design | E. Silva | Greensboro | 23 | 2026 | 28 | 2026 |  | Aligned |  | L4_Logistics-1
| 3 | Warehouse readiness | B. Haas | Greensboro | 29 | 2026 | 34 | 2026 |  | Planned |  | L4_Logistics-2
| 4 | Supplier ramp plan | B. Haas | Remote | 35 | 2026 | 40 | 2026 |  | Risk |  | L4_Logistics-3; L5_Supplier_B-3
| 5 | Logistics sign-off | E. Silva | Greensboro | 42 | 2026 | 46 | 2026 |  | TBD |  | L4_Logistics-4
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## L4 time plan
No. | Activity / Event | Responsible | Location | Status