## L5 input
Project Name |  | Demo Vehicle Programme | [10 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  | DVP-2026 | SoP | Wk 1, 2026 | [8 empty] | 1 | 2026 | 52 | 2030
Description |  | Tier-1 supplier B milestone plan. | [10 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  | L5 Supplier B Plan |  | Plan ID | L5_Supplier_B |  | Last updated | 2026-08-06
| No. | Activity / Event | Responsible | Location | Start Wk | Start Yr | End Wk | End Yr | Tracker | Status | Comments / Notes | Dependencies
| 1 | Nomination | U. Braun | Remote | 7 | 2026 | 11 | 2026 |  | Completed |  | L1_Programme-1
| 2 | Process audit | U. Braun | Pune | 12 | 2026 | 17 | 2026 |  | Aligned |  | L5_Supplier_B-1
| 3 | Sample submission | Z. Marek | Pune | 18 | 2026 | 25 | 2026 |  | Blocker |  | L5_Supplier_B-2
| 4 | Capacity verification | Z. Marek | Pune | 26 | 2026 | 33 | 2026 |  | Risk |  | L5_Supplier_B-3; L4_Logistics-3
| 5 | Series release | U. Braun | Pune | 35 | 2026 | 42 | 2026 |  | TBD |  | L5_Supplier_B-4
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## L5 time plan
No. | Activity / Event | Responsible | Location | Status