## L1 input
Project Name |  |  | Sample Project — Replace With Your Own Name | [11 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  |  | DEMO-001 | SoP | Wk 1, 2026 | [9 empty] | 1 | 2026 | 52 | 2030
Description |  |  | This is a demo timeplan. Each row below explains how to use one part of this template — replace this sample data with your real project details whenever you are ready. | [11 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  |  | L1 Programme Master Plan |  | Timeplan ID | L1_Master |  | Timeplan Owner |  |  |  |  | Last updated | 2026-08-18
| Colour | No. | Activity / Event | Responsible | Department | Location | Start Wk | Start Yr | End Wk | End Yr | Status | Tracker | Comments / Notes | Dependencies
| Blue | 1 | Concept & feasibility | E. Lindqvist | Manufacturing | Remote | 2 | 2026 | 36 | 2026 | Completed
| Blue | 2 | Design & development | H. Bergström | Test & Validation | Remote | 40 | 2026 | 24 | 2027 | Dependency
| Blue | 3 | Verification & validation | P. Nair | Engineering | Bangalore | 24 | 2027 | 6 | 2028 | Dependency
| Blue | 4 | Industrialisation | T. Nilsson | Quality | Ageo | 13 | 2028 | 47 | 2028 | Aligned
| Blue | 5 | Start of production | L. Andersson | Engineering | Curitiba | 50 | 2028 | 27 | 2029 | Planned
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L2 input
Project Name |  |  | Sample Project — Replace With Your Own Name | [11 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  |  | DEMO-001 | SoP | Wk 1, 2026 | [9 empty] | 1 | 2026 | 52 | 2030
Description |  |  | This is a demo timeplan. Each row below explains how to use one part of this template — replace this sample data with your real project details whenever you are ready. | [11 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  |  | L2 Workstream Plan |  | Timeplan ID | L2_Master |  | Timeplan Owner |  |  |  |  | Last updated | 2026-08-18
| Colour | No. | Activity / Event | Responsible | Department | Location | Start Wk | Start Yr | End Wk | End Yr | Status | Tracker | Comments / Notes | Dependencies
| Green | 1 | Requirements definition | R. Iyer | Purchasing | Gothenburg | 1 | 2026 | 10 | 2026 | Pending
| Green | 2 | System architecture freeze | H. Bergström | Quality | Greensboro | 24 | 2026 | 36 | 2026 | Pending
| Green | 3 | Thermal simulation package | J. Svensson | Logistics | Ageo | 42 | 2026 | 52 | 2026 | Planned
| Green | 4 | Supplier sourcing decision | K. Mehta | Manufacturing | Curitiba | 15 | 2027 | 31 | 2027 | Risk
| Green | 5 | Prototype build A-sample | S. Gupta | Quality | Curitiba | 35 | 2027 | 46 | 2027 | Not Achieved
| Green | 6 | Design verification testing | A. Sharma | Purchasing | Gothenburg | 3 | 2028 | 24 | 2028 | Aligned
| Green | 7 | Tooling release | S. Gupta | Programme Office | Gothenburg | 26 | 2028 | 41 | 2028 | Planned
| Green | 8 | Pilot production run | H. Bergström | Purchasing | Lyon | 47 | 2028 | 12 | 2029 | Blocker |  |  | L2_Master-6
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L3 input
Project Name |  |  | Sample Project — Replace With Your Own Name | [11 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  |  | DEMO-001 | SoP | Wk 1, 2026 | [9 empty] | 1 | 2026 | 52 | 2030
Description |  |  | This is a demo timeplan. Each row below explains how to use one part of this template — replace this sample data with your real project details whenever you are ready. | [11 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  |  | L3 Project Plan |  | Timeplan ID | L3_Master |  | Timeplan Owner |  |  |  |  | Last updated | 2026-08-18
| Colour | No. | Activity / Event | Responsible | Department | Location | Start Wk | Start Yr | End Wk | End Yr | Status | Tracker | Comments / Notes | Dependencies
| Yellow | 1 | Customer requirements review | T. Nilsson | Logistics | Curitiba | 1 | 2026 | 7 | 2026 | Completed
| Yellow | 2 | Concept sketch review | N. Desai | Test & Validation | Curitiba | 14 | 2026 | 24 | 2026 | Pending
| Yellow | 3 | CFD thermal analysis | P. Nair | Quality | Bangalore | 23 | 2026 | 26 | 2026 | Planned
| Yellow | 4 | Material selection | A. Sharma | Purchasing | Curitiba | 35 | 2026 | 44 | 2026 | To be discussed
| Yellow | 5 | Design freeze gate | R. Iyer | Purchasing | Curitiba | 48 | 2026 | 50 | 2026 | To be discussed |  |  | L3_Master-3
| Yellow | 6 | Prototype tooling design | V. Rao | Logistics | Bangalore | 6 | 2027 | 8 | 2027 | Completed
| Yellow | 7 | Prototype sample build | K. Mehta | Aftermarket | Lyon | 20 | 2027 | 27 | 2027 | Aligned
| Yellow | 8 | Bench test campaign | H. Bergström | Engineering | Ageo | 29 | 2027 | 33 | 2027 | Aligned
| Yellow | 9 | Vehicle integration test | E. Lindqvist | Purchasing | Remote | 43 | 2027 | 48 | 2027 | Dependency
| Yellow | 10 | Supplier PPAP submission | S. Gupta | Programme Office | Lyon | 52 | 2027 | 3 | 2028 | Aligned
| Yellow | 11 | Durability testing | R. Iyer | Programme Office | Greensboro | 13 | 2028 | 22 | 2028 | To be discussed
| Yellow | 12 | Cost optimisation review | V. Rao | Logistics | Bangalore | 23 | 2028 | 27 | 2028 | Pending
| Yellow | 13 | Production readiness review | J. Svensson | Manufacturing | Gothenburg | 36 | 2028 | 45 | 2028 | Planned |  |  | L3_Master-11
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L4 input
Project Name |  |  | Sample Project — Replace With Your Own Name | [11 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  |  | DEMO-001 | SoP | Wk 1, 2026 | [9 empty] | 1 | 2026 | 52 | 2030
Description |  |  | This is a demo timeplan. Each row below explains how to use one part of this template — replace this sample data with your real project details whenever you are ready. | [11 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  |  | L4 Team Plan |  | Timeplan ID | L4_Master |  | Timeplan Owner |  |  |  |  | Last updated | 2026-08-18
| Colour | No. | Activity / Event | Responsible | Department | Location | Start Wk | Start Yr | End Wk | End Yr | Status | Tracker | Comments / Notes | Dependencies
| Purple | 1 | Project kickoff | M. Karlsson | Manufacturing | Lyon | 3 | 2026 | 11 | 2026 | Blocker
| Purple | 2 | Requirements workshop | L. Andersson | Quality | Curitiba | 13 | 2026 | 18 | 2026 | Aligned
| Purple | 3 | Initial CAD layout | N. Desai | Purchasing | Bangalore | 19 | 2026 | 21 | 2026 | Planned
| Purple | 4 | Thermal model v1 | A. Sharma | Aftermarket | Lyon | 31 | 2026 | 37 | 2026 | Pending |  |  | L4_Master-2
| Purple | 5 | Design review 1 | P. Nair | Logistics | Remote | 40 | 2026 | 47 | 2026 | To be discussed
| Purple | 6 | Bracket structural analysis | M. Karlsson | Manufacturing | Lyon | 50 | 2026 | 2 | 2027 | Planned
| Purple | 7 | Prototype part order | V. Rao | Engineering | Lyon | 10 | 2027 | 12 | 2027 | Blocker
| Purple | 8 | Sensor calibration | A. Sharma | Logistics | Lyon | 20 | 2027 | 28 | 2027 | Completed
| Purple | 9 | Bench rig setup | R. Iyer | Aftermarket | Gothenburg | 28 | 2027 | 37 | 2027 | Completed |  |  | L4_Master-7
| Purple | 10 | Thermal cycle test | K. Mehta | Engineering | Bangalore | 41 | 2027 | 43 | 2027 | Completed
| Purple | 11 | Vibration test | E. Lindqvist | Test & Validation | Remote | 49 | 2027 | 52 | 2027 | Risk
| Purple | 12 | EMC test | K. Mehta | Programme Office | Remote | 6 | 2028 | 10 | 2028 | Planned
| Purple | 13 | Supplier audit | S. Gupta | Quality | Curitiba | 15 | 2028 | 24 | 2028 | Deferred
| Purple | 14 | FMEA update | H. Bergström | Quality | Gothenburg | 27 | 2028 | 33 | 2028 | Not Achieved |  |  | L4_Master-12
| Purple | 15 | Assembly line trial run | R. Iyer | Manufacturing | Remote | 37 | 2028 | 46 | 2028 | Completed
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L5 input
Project Name |  |  | Sample Project — Replace With Your Own Name | [11 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code |  |  | DEMO-001 | SoP | Wk 1, 2026 | [9 empty] | 1 | 2026 | 52 | 2030
Description |  |  | This is a demo timeplan. Each row below explains how to use one part of this template — replace this sample data with your real project details whenever you are ready. | [11 empty] | Timeplan range |  |  |  | Today
Timeplan Name |  |  | L5 Task Plan |  | Timeplan ID | L5_Master |  | Timeplan Owner |  |  |  |  | Last updated | 2026-08-18
| Colour | No. | Activity / Event | Responsible | Department | Location | Start Wk | Start Yr | End Wk | End Yr | Status | Tracker | Comments / Notes | Dependencies
| Red | 1 | Draft specification | J. Svensson | Test & Validation | Greensboro | 3 | 2026 | 10 | 2026 | Risk
| Red | 2 | Circulate for review | A. Sharma | Engineering | Gothenburg | 9 | 2026 | 16 | 2026 | Planned
| Red | 3 | Incorporate feedback | K. Mehta | Logistics | Lyon | 16 | 2026 | 21 | 2026 | Deferred
| Red | 4 | Finalise specification | C. Fernandes | Logistics | Ageo | 24 | 2026 | 29 | 2026 | Pending
| Red | 5 | CAD model housing | N. Desai | Test & Validation | Bangalore | 29 | 2026 | 36 | 2026 | Planned
| Red | 6 | CAD model bracket | A. Sharma | Quality | Lyon | 38 | 2026 | 48 | 2026 | Completed |  |  | L5_Master-4
| Red | 7 | CAD model sensor mount | K. Mehta | Programme Office | Remote | 48 | 2026 | 4 | 2027 | Planned
| Red | 8 | Tolerance stack-up check | C. Fernandes | Manufacturing | Bangalore | 3 | 2027 | 7 | 2027 | Aligned
| Red | 9 | Thermal simulation case A | N. Desai | Programme Office | Greensboro | 10 | 2027 | 13 | 2027 | Pending |  |  | L5_Master-7
| Red | 10 | Thermal simulation case B | T. Nilsson | Purchasing | Greensboro | 18 | 2027 | 22 | 2027 | Aligned |  |  | L5_Master-8
| Red | 11 | Thermal simulation case C | M. Karlsson | Purchasing | Greensboro | 22 | 2027 | 29 | 2027 | Completed |  |  | L5_Master-9
| Red | 12 | Order prototype parts | J. Svensson | Programme Office | Remote | 33 | 2027 | 38 | 2027 | Aligned
| Red | 13 | Incoming parts inspection | S. Gupta | Logistics | Remote | 38 | 2027 | 43 | 2027 | Aligned |  |  | L5_Master-11
| Red | 14 | Assemble prototype | P. Nair | Manufacturing | Gothenburg | 47 | 2027 | 2 | 2028 | Blocker
| Red | 15 | Bench test run 1 | K. Mehta | Engineering | Lyon | 3 | 2028 | 6 | 2028 | Aligned
| Red | 16 | Bench test run 2 | A. Sharma | Test & Validation | Ageo | 8 | 2028 | 12 | 2028 | Blocker
| Red | 17 | Bench test run 3 | M. Karlsson | Manufacturing | Ageo | 17 | 2028 | 21 | 2028 | Not Achieved
| Red | 18 | Data analysis | V. Rao | Test & Validation | Ageo | 23 | 2028 | 26 | 2028 | Aligned
| Red | 19 | Report writing | M. Karlsson | Logistics | Remote | 34 | 2028 | 43 | 2028 | Planned
| Red | 20 | Stakeholder sign-off | T. Nilsson | Quality | Bangalore | 40 | 2028 | 43 | 2028 | To be discussed
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L3 time plan
No. | Activity / Event | Responsible | Location | Status

## master time plan
Master Timeplan Range
[6 empty] | Start Wk | Start Yr | End Wk | End Yr
Level | No. | Activity / Event | Responsible | Location | Status | Today
L1
L2
L3
L4
L5