## L3 description
Project Name | Demo Vehicle Programme | [6 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code | DVP-2026 | SoP | Wk 1, 2026 |  |  |  |  | 1 | 2026 | 52 | 2030
Description | Tooling sub-plan. | [6 empty] | Timeplan range |  |  |  | Today
Timeplan Name | L3 Tooling Plan |  | Timeplan ID | L3_Tooling | Timeplan Owner | Last updated | 2026-08-18

## L3 input
Colour (Planned) | Colour (Actual) | No. | Activity / Event | Responsible | Department | Location | Planned Start Wk | Planned Start Yr | Planned End Wk | Planned End Yr | Actual Start Wk | Actual Start Yr | Actual End Wk | Actual End Yr | Status | Tracker | Comments / Notes | Dependencies
Yellow | Red | 1 | Tooling concept study | T. Nilsson | Tooling | Curitiba | 1 | 2026 | 6 | 2026 | 2 | 2026 | 8 | 2026 | Not Achieved |  | Coordinating with adjacent workstream on timing.
Yellow | Green | 2 | Die face design | N. Desai | Tooling | Curitiba | 7 | 2026 | 11 | 2026 | 7 | 2026 | 10 | 2026 | Pending |  | Risk noted, mitigation plan in progress. | L2_Bodyshop-3
Yellow | Yellow | 3 | Tool steel order | N. Desai | Tooling | Greensboro | 17 | 2026 | 19 | 2026 |  |  |  |  | Pending |  | Data still being validated with the plant.
Yellow | Yellow | 4 | Rough machining | V. Rao | Tooling | Gothenburg | 24 | 2026 | 32 | 2026 |  |  |  |  | Blocker |  | Kickoff meeting scheduled, agenda to follow.
Yellow | Yellow | 5 | Finish machining | V. Rao | Tooling | Curitiba | 31 | 2026 | 35 | 2026 |  |  |  |  | Aligned |  | Budget approved, purchase order in process.
Yellow | Yellow | 6 | Tryout run 1 | N. Desai | Tooling | Bangalore | 38 | 2026 | 42 | 2026 |  |  |  |  | Blocker |  | Design under review, feedback expected shortly.
Yellow | Yellow | 7 | Tryout run 2 | T. Nilsson | Tooling | Remote | 47 | 2026 | 1 | 2027 |  |  |  |  | Planned |  | Held pending customer confirmation.
Yellow | Yellow | 8 | Surface hardening | V. Rao | Tooling | Remote | 2 | 2027 | 7 | 2027 |  |  |  |  | Aligned |  | Trial run scheduled for next milestone.
Yellow | Yellow | 9 | Tool transfer to plant | V. Rao | Tooling | Greensboro | 9 | 2027 | 15 | 2027 |  |  |  |  | Blocker |  | Documentation being finalised for handover. | L2_Bodyshop-6
Yellow | Yellow | 10 | Installation in press | T. Nilsson | Tooling | Bangalore | 14 | 2027 | 17 | 2027 |  |  |  |  | Risk |  | Awaiting test results from the lab.
Yellow | Yellow | 11 | Production tryout | V. Rao | Tooling | Greensboro | 22 | 2027 | 28 | 2027 |  |  |  |  | Risk |  | Logistics plan confirmed with carrier.
Yellow | Yellow | 12 | Dimensional sign-off | V. Rao | Tooling | Lyon | 29 | 2027 | 31 | 2027 |  |  |  |  | Planned |  | Staffing plan under discussion with HR.
Yellow | Yellow | 13 | Tool handover | V. Rao | Tooling | Gothenburg | 39 | 2027 | 45 | 2027 |  |  |  |  | Pending |  | No update since last review.
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L3 time plan
No. | Activity / Event | Responsible | Department | Location | Status | Tracker | Comments / Notes