## L4 description
Project Name | Demo Vehicle Programme | [6 empty] | Start Wk | Start Yr | End Wk | End Yr | Current Wk | Current Yr
Project Code | DVP-2026 | SoP | Wk 1, 2026 |  |  |  |  | 1 | 2026 | 52 | 2030
Description | Final assembly detail plan. | [6 empty] | Timeplan range |  |  |  | Today
Timeplan Name | L4 Assembly Plan |  | Timeplan ID | L4_Assembly | Timeplan Owner | Last updated | 2026-08-18

## L4 input
Colour (Planned) | Colour (Actual) | No. | Activity / Event | Responsible | Department | Location | Planned Start Wk | Planned Start Yr | Planned End Wk | Planned End Yr | Actual Start Wk | Actual Start Yr | Actual End Wk | Actual End Yr | Status | Tracker | Comments / Notes | Dependencies
Purple | Blue | 1 | Assembly sequence study | H. Bergström | Assembly Engineering | Remote | 1 | 2026 | 9 | 2026 | 2 | 2026 | 11 | 2026 | Risk |  | Awaiting sign-off from the regional lead before this can move forward.
Purple | Green | 2 | Station layout draft | H. Bergström | Assembly Engineering | Greensboro | 6 | 2026 | 11 | 2026 | 6 | 2026 | 9 | 2026 | Aligned |  | Vendor confirmed capacity; no blockers expected at this stage.
Purple | Purple | 3 | Ergonomics review | J. Svensson | Assembly Engineering | Curitiba | 14 | 2026 | 19 | 2026 |  |  |  |  | Pending |  | Scope agreed in principle, final numbers pending next review.
Purple | Purple | 4 | Torque tool selection | J. Svensson | Assembly Engineering | Greensboro | 21 | 2026 | 25 | 2026 |  |  |  |  | To be discussed |  | Tooling still being fitted, minor delay possible.
Purple | Purple | 5 | Fixture concept | H. Bergström | Assembly Engineering | Greensboro | 28 | 2026 | 30 | 2026 |  |  |  |  | Blocker |  | Cross-checked with supplier schedule, dates look achievable.
Purple | Purple | 6 | Fixture build | J. Svensson | Assembly Engineering | Lyon | 33 | 2026 | 38 | 2026 |  |  |  |  | Completed |  | Waiting on parts delivery, follow up next week. | L3_Tooling-6
Purple | Purple | 7 | Conveyor modification | A. Sharma | Assembly Engineering | Lyon | 38 | 2026 | 46 | 2026 |  |  |  |  | Risk |  | Draft plan circulated for comment.
Purple | Purple | 8 | Station 10 build | H. Bergström | Assembly Engineering | Gothenburg | 46 | 2026 | 49 | 2026 |  |  |  |  | Risk |  | Site readiness confirmed by local team.
Purple | Purple | 9 | Station 20 build | J. Svensson | Assembly Engineering | Remote | 1 | 2027 | 6 | 2027 |  |  |  |  | Pending |  | Change request logged, awaiting approval.
Purple | Purple | 10 | Station 30 build | J. Svensson | Assembly Engineering | Lyon | 7 | 2027 | 15 | 2027 |  |  |  |  | Dependency |  | On track, no open issues at present.
Purple | Purple | 11 | Software integration | A. Sharma | Assembly Engineering | Greensboro | 12 | 2027 | 17 | 2027 |  |  |  |  | Aligned |  | Resourcing gap flagged to programme office. | L3_Tooling-11
Purple | Purple | 12 | Dry-cycle testing | J. Svensson | Assembly Engineering | Lyon | 21 | 2027 | 26 | 2027 |  |  |  |  | Blocker |  | Dependent activity slipped, watching closely.
Purple | Purple | 13 | Operator training | J. Svensson | Assembly Engineering | Bangalore | 27 | 2027 | 30 | 2027 |  |  |  |  | Risk |  | Quality checklist updated ahead of gate review.
Purple | Purple | 14 | Pre-series run | J. Svensson | Assembly Engineering | Greensboro | 31 | 2027 | 38 | 2027 |  |  |  |  | Dependency |  | Coordinating with adjacent workstream on timing.
Purple | Purple | 15 | Line release | H. Bergström | Assembly Engineering | Remote | 40 | 2027 | 47 | 2027 |  |  |  |  | Aligned |  | Risk noted, mitigation plan in progress.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## L4 time plan
No. | Activity / Event | Responsible | Department | Location | Status | Tracker | Comments / Notes